## Sheet1
Task | Start | End | Days | % Done
Gathering related papers | Mon 9/02/24 | Thu 9/05/24 | 4 | 100%
Review literatures | Fri 9/06/24 | Mon 9/09/24 | 2 | 100%
Documenting | Tue 9/10/24 | Wed 9/11/24 | 2 | 100%
Powerpoint Presentation | Thu 9/12/24 | Fri 9/13/24 | 2 | 100%
Reviewing the data | Mon 9/16/24 | Mon 9/16/24 | 1 | 100%
Identifying relationship in the data | Tue 9/17/24 | Tue 9/17/24 | 1 | 100%
Analyze the data | Wed 9/18/24 | Fri 9/20/24 | 3 | 100%
Identify the important features or variables | Mon 9/23/24 | Tue 9/24/24 | 2 | 100%
Plan for the API architecture | Wed 9/25/24 | Fri 9/27/24 | 3 | 100%
Perform feature engineering(e.g.: combine soil and weather data) | Mon 9/30/24 | Fri 10/04/24 | 5 | 50%
Split the data | Mon 10/07/24 | Tue 10/08/24 | 2 | 0%
Set up the structure of FastAPI with routing and data models | Wed 10/09/24 | Fri 10/11/24 | 3 | 0%
Select the models | Mon 10/14/24 | Wed 10/16/24 | 3 | 0%
Train different models and compare their performance | Thu 10/17/24 | Fri 10/18/24 | 2 | 0%
Fine-tune hyperparameters | Mon 10/21/24 | Tue 10/22/24 | 2 | 0%
Develop API endpoints for model training, testing, and evaluation | Wed 10/23/24 | Thu 10/24/24 | 2 | 0%
Evaluate models with different metrics | Fri 10/25/24 | Tue 10/29/24 | 3 | 0%
Select the best model | Wed 10/30/24 | Fri 11/01/24 | 3 | 0%
Implement API endpoints for real-time predictions and recommendations based on the inputs parameters | Mon 11/04/24 | Wed 11/06/24 | 3 | 0%
Deploy the API to the server | Thu 11/07/24 | Fri 11/08/24 | 2 | 0%
Document the APIs | Mon 11/11/24 | Tue 11/12/24 | 2 | 0%
Unit testing | Wed 11/13/24 | Fri 11/15/24 | 3 | 0%
Integration testing | Mon 11/18/24 | Wed 11/20/24 | 3 | 0%
Collect feedback from backend developers and refine APIs | Thu 11/21/24 | Mon 11/25/24 | 3 | 0%
Document the APIs using postman | Tue 11/26/24 | Wed 11/27/24 | 2 | 0%
Conduct final review | Thu 11/28/24 | Mon 12/02/24 | 3 | 0%
Prepare a presentation | Tue 12/03/24 | Wed 12/04/24 | 2 | 0%
This chart isn’t available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn’t available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet2
Task | Sprint 1 (Done) |  | Sprint 2 (Done) |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7
| Mon 9/02/24 | Fri 9/13/24 | Mon 9/16/24 | Fri 9/27/24 | Mon 9/30/24 | Thu 10/24/24 | Fri 10/25/24 | Wed 11/06/24 | Thu 11/07/24 | Tue 11/12/24 | Wed 11/13/24 | Wed 11/20/24 | Tue 11/26/24 | Mon 12/02/24
Gathering related papers | 28
Review literatures | 14
Documenting | 14
Powerpoint Presentation | 14
Reviewing the data |  |  | 7
Identifying relationship in the data |  |  | 7
Analyze the data |  |  | 21
Identify the important features or variables |  |  | 14
Plan for the API architecture |  |  | 21
Perform feature engineering(e.g.: combine soil and weather data) |  |  |  |  | 35
Split the data |  |  |  |  | 14
Set up the structure of FastAPI with routing and data models |  |  |  |  | 21
Select the models |  |  |  |  | 21
Train different models and compare their performance |  |  |  |  | 14
Fine-tune hyperparameters |  |  |  |  | 14
Develop API endpoints for model training, testing, and evaluation |  |  |  |  | 14
Evaluate models with different metrics | [6 empty] | 21
Select the best model | [6 empty] | 21
Implement API endpoints for real-time predictions and recommendations based on the inputs parameters | [6 empty] | 21
Deploy the API to the server | [8 empty] | 14
Document the APIs | [8 empty] | 14
Unit testing | [10 empty] | 21
Integration testing | [10 empty] | 21
Collect feedback from backend developers and refine APIs | [10 empty] | 21
Document the APIs using postman | [12 empty] | 14
Conduct final review | [12 empty] | 21
Prepare a presentation | [12 empty] | 14